## Test Plan
Introduction
With the desire to bring customers quality products and the best experience.The Test Plan has been created to facilitate communication within the team members. This document describe approaches and methodologies that will apply to the unit, integration and system testing of the "https://social-network.warface.codegym.vn/".
1. Functional requirements to perform test: - Login - Register - Forgot password - Search - Search default - Search advance - Group - Group list - Group timeline - Group member - Group warning - Group participate - Newsfeed - My page - Other's page - Friend's page - Edit profile - Edit profile - Change avatar - Change password - Edit status - Common - Header - Friend requests - Advertisement - Chat - Create post - Post list - Comment, Reply, List - Common error message - Intergration 2. Non-functional system testing: - Usability - Sercurity 3. Eviroment to test: - Link: https://social-network.warface.codegym.vn/login - Devices: Laptop - Browsers: Chrome, Firefox
Not in scope
- Automation Test is not considered in the Plan - Multiple languages is not considered in the Plan - No API Test - No Perfomance test
Tools test
Test Plan : Google sheet Test Case: Google sheet Tool to capture error images: Snapgit, Lightshot,.. Tool to track bugs: Redmine Test report: Google sheet
Test approach
1. Create spec: Since there is no requirement available, we will create the spec on legacy product te spec page by page - Define common features which is using in multiple page - Define a spec for common validation, common UI/UX rules 2. Prepare test case: UT, IT (ST will be conducted by another team) - Once the spec is reviewed and approved by customer the test case preparation will be offically started - Create test design first, then implement test case detail 3. Review: - Peer review by checklist - High level review by Leader 4. Method of using resources: - The members are expected to ensure their own work and cross-check 5. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thủy |  | Test Lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business - Review bug
2 | Vân Anh |  | Tester |  | -Write Requirement - Write Test case - Write Test case for intergration test - Test UI - Test Function - Cross-check
3 | Others |  | Tester |  | -Write Requirement - Write Test case - Write Test case for intergration test - Test UI - Test Function - Cross-check
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan+ Estimate | 3 | Test leader/Tester | Test plan+ Estimate | 45224
2 | Requirement | 47 | Tester | Requirement | 45227
3 | Review Requirement | 30.5 | Tester | Comment | 45229
4 | Test case | 55 | Tester | Test case | 45231
5 | Review Test case | 36 | Tester | Comment | 45234
6 | Intergration testcase | 46.6 | Tester | Test case | 45236
7 | Review Intergration testcase | 46.6 | Tester | Comment | 45238
8 | Execution | 46.6 | Tester | Executed | 45241
9 | Log bug+ Report | 23.5 | Tester | Bug+ Report | 45243
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  | x | x | x
Functional Test |  |  | x | x | x
Performance Test
Usability test |  |  | x | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent |  |  | - End of Sprint - At the requests of Project Manager or superiors

## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Shopping online |  |  | Creator
Project Code | CG_SO |  |  | Reviewer/Approver
Document Code | CG_SO_XXX_vx.x |  |  | Issue Date
|  |  |  | Version | 1.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2021-11-07 | 1.0 |  | A | Tạo mới file | <List of documents which are referred in this version.>
30/7/2021 | 1.1 |  | M | Update ...

## Estimate
ESTIMATE DỰ ÁN TINDER
Pages | Sub-feature | Requirement | Review Requirement | Update | Testcase | Review Testcase | Update | Integration Testcase | Review Integration Testcase | Test | Log bug | Phân tích bug & Report
Login | Login | 1.5 | 0.75 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
Register | Register | 3.5 | 2 | 2 | 6 | 4 | 2.5 |  |  | 4 | 1.5
ForgotPass | ForgotPass | 2 | 1.5 | 0.5 | 2 | 2 | 0.5 |  |  | 1 | 1
Search | Search - default + Advance | 3 | 2.5 | 1.5 | 3.5 | 4 | 2 |  |  | 2 | 1.5
Group | Danh sách nhóm + Group Timeline | 3 | 1.5 | 1.5 | 4 | 2 | 2 |  |  | 2.5 | 2
| Group - Member + Warning + Participate | 4 | 2.5 | 2.5 | 5 | 2.5 | 2 |  |  | 3 | 2
Newsfeed | Newsfeed | 2 | 1.5 | 0.5 | 3 | 2 | 1 |  |  | 3 | 0.5
My Pages | My Pages | 4 | 2 | 1 | 5 | 4 | 2 |  |  | 4 | 1
Other's Pages | Other's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.5
Friend's Pages | Friend's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.75
Edit Profile | Edit Profile | 2 | 1.5 | 1.5 | 2 | 1 | 1 |  |  | 2 | 1
| Change Avatar | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 |  |  | 1 | 1
| Change Password | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
| Change Status | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
Common | Header | 1 | 0.75 | 0.75 | 1 | 1 | 0.5 |  |  | 1 | 1
| Friends suggest | 2 | 1 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 1
| Advertisment | 1 | 0.5 | 0.25 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
| Chat | 2 | 1.5 | 1 | 2.5 | 2 | 1 |  |  | 2 | 1
| Create Post | 2 | 1.5 | 1 | 1.5 | 1 | 1 |  |  | 3 | 1.5
| Post List | 2 | 1 | 1.5 | 2 | 1.5 | 1.5 |  |  | 3 | 1.5
| Comment + Reply + List | 3 | 2.5 | 2.75 | 3 | 2.5 | 2.75 |  |  | 2.5 | 1.5
Total |  | 47 | 30.5 | 23.75 | 55 | 36 | 24.75 | 0 | 0 | 46.5 | 23.25 | 0

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub total | #REF! | #REF! | #REF! | #REF! | #REF!
| Test coverage |  | #REF! | %
| Test successful coverage |  | #REF! | %