## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Shopping online |  |  | Creator
Project Code | CG_SO |  |  | Reviewer/Approver
Document Code | CG_SO_XXX_vx.x |  |  | Issue Date
|  |  |  | Version | 1.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2021-11-07 | 1.0 |  | A | Tạo mới file | <List of documents which are referred in this version.>
30/7/2021 | 1.1 |  | M | Update ...

## Test Plan
Scope of testing
1. Functional requirements to perform test: - Login - Register - Forgot password - Search - Group - Add friends - Newsfeed - My pages - Other's pages - Friend's pages - Edit Profile 2. Non-functional system testing: - Perfomance - Usablity 3. Eviroment to test: - Server test: https://social-network.warface.codegym.vn/login - Devices: Laptop HP 348 G5 - Browsers: Chrome
Tools Test
Test Plan : Google sheet Test Case: Google sheet Tool to capture error images: Snapgit, Lightshot,.. Tool to track bugs: Redmine Test report: Google sheet Test sercurity: Burn Suite
Test approach
1. Method of building test case: - All functions and business of the system must write test cases 2. Method of using resources: - ThuyDL: review the group project - All member in the tester team: Test API, Test Functions, Test UI, Test Performance 3. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thuy DL |  | BA/Qc lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business
2 | Phuong DT |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
3 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan Estimate | 3 | Test Leader | Test plan | 2023-10-24
2 | Requirement | 47 | Tester | Requirement | 2023-10-26
3 | Test Case | 55 | Tester | Test case | 2023-10-29
4 | Execution | 46,5 | Tester | Test execution | 2023-11-01
5 | Report | 20,1 | Tester | Test report | 2023-08-19
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  |  | x | x | x
Functional Test |  |  | x | x | x | x
Performance Test |  |  |  |  | x | x
Usability test |  |  |  |  | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent |  |  | - End the Sprint - At the request of Project manager or superiors

## Estimate
Pages | Sub-feature | Req | Review Req | Update | TC | Review TC | Update | Integration TC | Review Integration TC | Test | log bug | Phân tích bug & Report
Login | Login | 1.5 | 0.75 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
Register | Register | 3.5 | 2 | 2 | 6 | 4 | 2.5 |  |  | 4 | 1.5
ForgotPass | ForgotPass | 2 | 1.5 | 0.5 | 2 | 2 | 0.5 |  |  | 1 | 1
Search | Search - default + Advance | 3 | 2.5 | 1.5 | 3.5 | 4 | 2 |  |  | 2 | 1.5
Group | Danh sách nhóm + Group Timeline | 3 | 1.5 | 1.5 | 4 | 2 | 2 |  |  | 2.5 | 2
| Group - Member + Warning + Participate | 4 | 2.5 | 2.5 | 5 | 2.5 | 2 |  |  | 3 | 2
Newsfeed | Newsfeed | 2 | 1.5 | 0.5 | 3 | 2 | 1 |  |  | 3 | 0.5
My Pages | My Pages | 4 | 2 | 1 | 5 | 4 | 2 |  |  | 4 | 1
Other's Pages | Other's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.5
Friend's Pages | Friend's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.75
Edit Profile | Edit Profile | 2 | 1.5 | 1.5 | 2 | 1 | 1 |  |  | 2 | 1
| Change Avatar | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 |  |  | 1 | 1
| Change Password | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
| Change Status | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
Common | Header | 1 | 0.75 | 0.75 | 1 | 1 | 0.5 |  |  | 1 | 1
| Friends suggest | 2 | 1 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 1
| Advertisment | 1 | 0.5 | 0.25 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
| Chat | 2 | 1.5 | 1 | 2.5 | 2 | 1 |  |  | 2 | 1
| Create Post | 2 | 1.5 | 1 | 1.5 | 1 | 1 |  |  | 3 | 1.5
| Post List | 2 | 1 | 1.5 | 2 | 1.5 | 1.5 |  |  | 3 | 1.5
| Comment + Reply + List | 3 | 2.5 | 2.75 | 3 | 2.5 | 2.75 |  |  | 2.5 | 1.5
Total |  | 47 | 30.5 | 23.75 | 55 | 36 | 24.75 | 0 | 0 | 46.5 | 23.25 | 0

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub total | #REF! | #REF! | #REF! | #REF! | #REF!
| Test coverage |  | #REF! | %
| Test successful coverage |  | #REF! | %