## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Tinder |  |  | Creator
Project Code | CG_SO |  |  | Reviewer/Approver
Document Code | CG_SO_v1.0 |  |  | Issue Date
|  |  |  | Version | 1.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
25/10/2023 | 1.0 |  | A | Tạo mới file | <List of documents which are referred in this version.>

## Test Plan
Scope of testing
1. Functional requirements to perform test: - Login - Register - Forgot password - Search - Group - Add friends - Newsfeed - My pages - Other's pages - Friend's pages - Edit Profile 2. Non-functional system testing: - Performance - Usability 3. Enviroment to test: - Server test: https://social-network.warface.codegym.vn/login - Devices: Macbook Pro version 12.7, Window version 10 - Browsers: Chrome, Safari
Tools Test
Test Plan : Google sheet Test Case: Google sheet Tool to capture error images: Lightshot, Screenpresso,... Tool to track bugs: Redmine Test report: Google sheet Test performance: Jmeter Test API: Postman
Test approach
1. Method of building test case: - All functions and business of the system must write test cases 2. Test Browser and the devices are classified according to the following stages: - FUT - Itegration test - System test 3. Method of using resources: - ThuyDL: BA, review TC - Vui, Yến, Thảo, Chinh, Vân Anh, Hà, Huy, Minh Anh, Chi, Uyên, Phương: Test API, Test Functions, Test UI/UX, Test Performance 4. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer
Resources
No. | Name |  | Role |  | Task
1 | ThuyDL |  | BA/Qc lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business |  | TAsk ở đây nếu tester giống nhau có thể gộp
|  |  | Tester |  | - Write requirement - Review requirement - Update requirement - Create Test case - Review Test case - Update Test case - Execute Test case - Log bug
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan | 5 | Test leader | Test plan | 10/23/2023
2 | Estimate | 2 | All members of project | Estimate document | 2023-10-24
3 | Requirement | 47 | Tester | SRS/URD | 2023-10-26 | Include (Create, Review, Update)
4 | Create Test Case | 55 | Tester | Test case | 2023-10-29 | Include Review and Update
5 | Execute Test Case | 46,5 | Tester | % Pass & %Fail | 2023-11-01
6 | Log bug | 23.25 | Tester | Link bug | 2023-02-11
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  |  | x | x | x
Functional Test |  |  | x | x | x | x
Performance Test |  |  |  |  | x | x
Usability test |  |  |  |  | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent |  |  | - When the bug changes its status to resolved - When there are changes in requirements - When requested by the customer

## Estimate detail
Pages | Sub-feature | Req | Review Req | Update | TC | Review TC | Update | Integration TC | Review Integration TC | Test | log bug | Phân tích bug & Report
Login | Login | 1.5 | 0.75 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5 |  | Vui
Register | Register | 3.5 | 2 | 2 | 6 | 4 | 2.5 |  |  | 4 | 1.5 |  | Vui
ForgotPass | ForgotPass | 2 | 1.5 | 0.5 | 2 | 2 | 0.5 |  |  | 1 | 1 |  | Yến
Search | Search - default + Advance | 3 | 2.5 | 1.5 | 3.5 | 4 | 2 |  |  | 2 | 1.5 |  | Yến
Group | Danh sách nhóm + Group Timeline | 3 | 1.5 | 1.5 | 4 | 2 | 2 |  |  | 2.5 | 2 |  | Thảo
| Group - Member + Warning + Participate | 4 | 2.5 | 2.5 | 5 | 2.5 | 2 |  |  | 3 | 2 |  | Thảo
Newsfeed | Newsfeed | 2 | 1.5 | 0.5 | 3 | 2 | 1 |  |  | 3 | 0.5 |  | Chinh
My Pages | My Pages | 4 | 2 | 1 | 5 | 4 | 2 |  |  | 4 | 1 |  | Chinh
Other's Pages | Other's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.5 |  | VanAnh
Friend's Pages | Friend's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.75 |  | VanAnh
Edit Profile | Edit Profile | 2 | 1.5 | 1.5 | 2 | 1 | 1 |  |  | 2 | 1 |  | Hà
| Change Avatar | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 |  |  | 1 | 1 |  | Huy
| Change Password | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1 |  | M.Anh
| Change Status | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1 |  | M.Anh
Common | Header | 1 | 0.75 | 0.75 | 1 | 1 | 0.5 |  |  | 1 | 1 |  | Uyên
| Friends suggest | 2 | 1 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 1 |  | Uyên
| Advertisment | 1 | 0.5 | 0.25 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5 |  | Phương
| Chat | 2 | 1.5 | 1 | 2.5 | 2 | 1 |  |  | 2 | 1 |  | Phương
| Create Post | 2 | 1.5 | 1 | 1.5 | 1 | 1 |  |  | 3 | 1.5 |  | Chi
| Post List | 2 | 1 | 1.5 | 2 | 1.5 | 1.5 |  |  | 3 | 1.5 |  | Chi
| Comment + Reply + List | 3 | 2.5 | 2.75 | 3 | 2.5 | 2.75 |  |  | 2.5 | 1.5 |  | Hà
Total |  | 47 | 30.5 | 23.75 | 55 | 36 | 24.75 | 0 | 0 | 46.5 | 23.25 | 0

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub total | #REF! | #REF! | #REF! | #REF! | #REF!
| Test coverage |  | #REF! | %
| Test successful coverage |  | #REF! | %