## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Tinder |  |  | Creator | nguyen le huy
Project Code | CG_SO |  |  | Reviewer/Approver | Dang Le Thuy
Document Code | CG_SO_XXX_vx.x |  |  | Issue Date | 45225
|  |  |  | Version | 1.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
45224 | 1.1 | 'Test Plan' | A | Add Test Plan sheet
45225 | 1.1 | Estimate | A | Add Estimate sheet

## Test Plan
Scope of testing
1. Functional system testing: - Login - Register - Add friends - Edit profile - Search - Forgot password - Newsfeed - My pages - Friend's pages - Other's pages - Group 2. Non-functional system testing: - Performance - Usability 3. Eviroment to test: - System test: https://social-network.warface.codegym.vn - Devices: PC (main), mobile (only check main function) (Iphone, Samsung) - Browsers: Chrome, Safari | [7 empty] | Đừng dùng gạch chân
Tools Test
Test Plan : Google sheet Test Case: Google sheet Test Database: My SQL Tool to capture error images: Snapgit, Lightshot, PrtSc button on the keyboard Tool to track bugs: Redmine Test report: Google sheet Test performance: JMeter Test sercurity: Burn Suite
Test approach
1. Method of building test case: - All functions and business of the system must write test cases 2. Method of using resources: - ThuyDL: review the whole group project - All member in the tester team write testcase, test Functions, test UI, test Performance and check/review other member testcase 3. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thuy DL |  | Test Leader |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business
2 | Huy |  | Tester |  | - Write Test case - Write Test case for intergration test - Test UI - Test Function - Test Performance - Review other test cases/ specs
3 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test UI - Test Function - Test Performance - Review other test cases/ specs
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan + Estimate | 3 | Test Leader | Test plan | 45223
2 | Requirement | 95.8 | Tester | Requirement | 45226
3 | Test case | 127.3 | Tester | Test case | 45228 |  | Ngày tháng định dạng gì thế
4 | Execution | 94.3 | Tester | Test report | 45231
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  |  | x | N/A | N/A
Functional Test |  |  | N/A | x | N/A | N/A
Performance Test |  |  |  |  | N/A | N/A
Usability test |  |  | N/A | x | N/A | N/A
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | -Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users.
When does test recurrent |  |  | - End of sprint - At the request of Project manager or superiors

## Estimate
Pages | Sub-feature | Req | Review Req | Update | TC | Review TC | Update | Integration TC | Review Integration TC | Test | log bug | Phân tích bug & Report
Login | Login | 1.5 | 0.75 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
Register | Register | 3.5 | 2 | 2 | 6 | 4 | 2.5 |  |  | 4 | 1.5
ForgotPass | ForgotPass | 2 | 1.5 | 0.5 | 2 | 2 | 0.5 |  |  | 1 | 1
Search | Search - default + Advance | 3 | 2.5 | 1.5 | 3.5 | 4 | 2 |  |  | 2 | 1.5
Group | Danh sách nhóm + Group Timeline | 3 | 1.5 | 1.5 | 4 | 2 | 2 |  |  | 2.5 | 2
| Group - Member + Warning + Participate | 4 | 2.5 | 2.5 | 5 | 2.5 | 2 |  |  | 3 | 2
Newsfeed | Newsfeed | 2 | 1.5 | 0.5 | 3 | 2 | 1 |  |  | 3 | 0.5
My Pages | My Pages | 4 | 2 | 1 | 5 | 4 | 2 |  |  | 4 | 1
Other's Pages | Other's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.5
Friend's Pages | Friend's Pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 |  |  | 1 | 0.75
Edit Profile | Edit Profile | 2 | 1.5 | 1.5 | 2 | 1 | 1 |  |  | 2 | 1
| Change Avatar | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 |  |  | 1 | 1
| Change Password | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
| Change Status | 2 | 1 | 0.5 | 3 | 0.5 | 1 |  |  | 3 | 1
Common | Header | 1 | 0.75 | 0.75 | 1 | 1 | 0.5 |  |  | 1 | 1
| Friends suggest | 2 | 1 | 1 | 1.5 | 1 | 0.5 |  |  | 1.5 | 1
| Advertisment | 1 | 0.5 | 0.25 | 1.5 | 1 | 0.5 |  |  | 1.5 | 0.5
| Chat | 2 | 1.5 | 1 | 2.5 | 2 | 1 |  |  | 2 | 1
| Create Post | 2 | 1.5 | 1 | 1.5 | 1 | 1 |  |  | 3 | 1.5
| Post List | 2 | 1 | 1.5 | 2 | 1.5 | 1.5 |  |  | 3 | 1.5
| Comment + Reply + List | 3 | 2.5 | 2.75 | 3 | 2.5 | 2.75 |  |  | 2.5 | 1.5
Total |  | 47 | 30.5 | 23.75 | 55 | 36 | 24.75 | 0 | 0 | 46.5 | 23.25 | 0

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub total | #REF! | #REF! | #REF! | #REF! | #REF!
| Test coverage |  | #REF! | %
| Test successful coverage |  | #REF! | %