## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Shopping online |  |  | Creator
Project Code | CG_SO |  |  | Reviewer/Approver
Document Code | CG_SO_XXX_vx.x |  |  | Issue Date
|  |  |  | Version | 1.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2021-11-07 | 1.0 |  | A | Tạo mới file | <List of documents which are referred in this version.>
30/7/2021 | 1.1 |  | M | Update ...

## Test Plan
Scope of testing
1. Functional requirements to perform test: - Login - Register - Forgot password - Search - Group - Newwsfeed - My pages - Other's Pages - Friend's Pages - Edit Profile - Common 2. Non-functional system testing: - Friendliness - Reliability 3. Enviroment to test: - Server test: https://social-network.warface.codegym.vn/login - Devices: Laptop - Browsers: Chrome
Tools Test
Test Plan : Google sheet Test Case: Google sheet Tool to capture error images: Bandicam Tool to track bugs: Redmine Test report: Google sheet
Test approach
1. Method of building test case: - All functions and business of the system must write test cases : unit testcase and integration testcase 2. Test Browser and the devices are classified according to the following stages: - FUT: - Integration test: - System test: 3. Method of using resources: - BA, review TC: All members - Test Functions, Test UI: All members 4. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thủy |  | BA/Qc lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business
2 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
3 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
4 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan+Estimate | 5 | Test leader | Test plan | 2023-10-25
2 | Create Requirement | 48 | Tester | Requirement | 2023-10-28
3 | Review requirement | 24.75 | Tester | Comment | 10/30/2023
4 | Create tescase | 68 | Tester | Test cases | 2023-01-11
5 | Review testcase | 45.5 | Tester | Comment | 2023-04-11
6 | Intergration testcase | 8 | Tester | Test cases | 2023-06-11
7 | Review intergration testcase | 5 | Tester | Comment | 2023-08-11
8 | Execution | 63.75 | Tester | Executed | 2023-11-11
9 | Log bug + Report | 43 | Tester | Bug + Report | 11/13/2023
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  | x | x
Functional Test |  |  | x | x
Performance Test |  |  |  |  | x
Usability test |  |  | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent |  |  | - End of sprint - At the request of Project manager or superiors

## Estimate
No. | Pages | Sub-feature | Requirement |  |  | Test Case |  |  | Executed |  |  | Report | Total
|  |  | Create Req | Review Req | Update Req | Create TC | Review TC | Update TC | Test | Log bug | Phân tích bug | Report | (h) | (md)
1 | Login | Login | 2 | 1.5 | 1 | 2 | 1.5 | 1 | 1.5 | 0.5 | 0.5 | 0.5 | 10.5 | 1.3125
2 | Register | Register | 4 | 4 | 2 | 6 | 4 | 3 | 4.5 | 1.5 | 1.5 | 1.5 | 32 | 4
3 | Forgot password | Forgot password | 1 | 0.75 | 0.5 | 3 | 2 | 1 | 1.5 | 0.5 | 0.5 | 0.5 | 11.25 | 1.4062
4 | Search | - Search default - Search advance | 3 | 1.5 | 1.5 | 4 | 3 | 2 | 3 | 1 | 1 | 1 | 21 | 2.625
5 | Group | - Danh sách nhóm - Group timeline | 3 | 1.5 | 1.5 | 4 | 3 | 2 | 3 | 1 | 1 | 1 | 21 | 2.625
|  | - Group member - Group warning - Group participate | 5 | 2.5 | 2.5 | 6 | 4 | 3 | 5.25 | 1.75 | 1.75 | 1.5 | 33.25 | 4.1562
6 | Newsfeed | Newsfeed | 1 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 0.5 | 0.5 | 0.5 | 7.5 | 0.9375
7 | My page | My Pages | 4 | 2 | 2 | 5 | 3 | 2 | 4.5 | 1.5 | 1.5 | 1.5 | 27 | 3.375
8 | Other's pages | Other's pages | 4 | 2 | 2 | 5 | 3 | 2 | 4.5 | 1.5 | 1.5 | 1.5 | 27 | 3.375
9 | Friend's pages | Friend's pages | 3 | 1.5 | 1.5 | 4 | 3 | 2 | 4.5 | 1.5 | 1.5 | 1.5 | 24 | 3
10 | Edit Profile | Edit profile | 3 | 1 | 1 | 4 | 3 | 2 | 3.75 | 1.25 | 1.25 | 1.25 | 21.5 | 2.6875
|  | Change avatar | 1 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 0.5 | 0.5 | 0.5 | 7.5 | 0.9375
|  | Change password | 1.5 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 2.25 | 0.75 | 0.75 | 0.75 | 8 | 1
|  | Edit status | 1 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 0.5 | 0.5 | 0.5 | 7.5 | 0.9375
11 | Common | Header | 2 | 1 | 1 | 2 | 1.5 | 1 | 2.25 | 0.75 | 0.75 | 0.5 | 12.75 | 1.5938
|  | Friend requests | 2 | 1 | 1 | 2 | 1 | 1 | 2.25 | 0.75 | 0.75 | 0.5 | 12.25 | 1.5312
|  | Advertisment | 1 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 0.5 | 0.5 | 0.5 | 7.5 | 0.9375
|  | Chat | 1 | 0.5 | 0.5 | 1 | 0.75 | 0.75 | 1.5 | 0.5 | 0.5 | 0.5 | 7.5 | 0.9375
|  | Create post | 2 | 1 | 1 | 2 | 1 | 0.75 | 2.25 | 0.75 | 0.75 | 0.75 | 12.25 | 1.5312
|  | Post list | 2 | 1 | 1 | 2 | 1 | 0.75 | 2.25 | 1 | 0.75 | 0.75 | 12.5 | 1.5625
|  | - Comment - Reply - List | 2 | 1 | 1 | 2 | 1.5 | 1 | 2.25 | 1 | 0.75 | 0.75 | 13.25 | 1.6562
|  | Common error message | 1 | 0 | 0 | 1 | 0.5 | 0.3 | 0.75 | 0.25 | 0.25 | 0.25 | 4.3 | 0.5375
12 | Intergration | Intergration | 0 | 0 | 0 | 8 | 5 | 2 | 6 | 2 | 2 | 2 | 27 | 3.375
Total |  |  | 48 | 24.75 | 23.5 | 68 | 45.5 | 31.3 | 63.75 | 21.75 | 21.25 | 20.5 | 368.3 | 46.0375

## Test case List (hidden)
TEST CASE LIST
Project Name |  | Codegym_Tester_Shopping online
Project Code |  | CG_SO
Test Environment Setup Description |  | <List enviroment requires in this system 1. Server 2. Database 3. Web Browser ... >
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Mail list | MailList
2 | Login | Sheet2
3 | Function C | Sheet3
4 | Function D | Sheet4
5 | Function E | Sheet5

## Template (hidden)
Module Code | Module1 | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 1 | 4 | 0 | 6 | [6 empty] | N/A
ID | Group Name | Sub Group Name | Test Case Description | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
Module1 -1 | <group of test case = big function> | <group of test case = medium function> | <group of test case = small function> |  | <Describe steps to perform this case> |  | <Describe results which meet customer's requirement> | Pass
Module1 -2 | Check display email | [6 empty] | Fail
Module1 -3
Module1 -4
Module1 -5
Module1 -6

## Template Intergration test (hidden)
Module Code | Tinder | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 1 | 3 | 0 | 5 | [6 empty] | N/A
TS_ID | Test scenario name | TC_ID | Test Case name | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
Tinder-1 | Check tích hợp giữa màn hình Thêm mới user và màn hình login | 1 | Login thành công sau khi thêm mới tài khoản admin | - Đã tồn tại tài khoản admin: admin@codegym.vn Chưa có tk admin: thuy12@gmail.com | 1. Login bằng tk admin: admin@codegym.vn 2. Tại màn hình Thêm mới người dùng, tạo 1 tài khoản admin thuy12@gmail.com/123456 3. Log out 4. Đăng nhập với tài khoản thuy12@gmail.com/123456 |  | 1. Login thành công 2. Thêm mới tài khoản user thành công 3. Ra màn hình login 4. Đăng nhập thành công, hiển thị toàn bộ chức năng của hệ thống. | Pass
|  | 2 | Login thành công sau khi thêm mới tài khoản user | - Đã tồn tại tài khoản admin: admin@codegym.vn Chưa có tk user: thuy_user@gmail.com | 1. Login bằng tk admin: admin@codegym.vn 2. Tại màn hình Thêm mới người dùng, tạo 1 tài khoản user thuy_user@gmail.com/123456 3. Log out 4. Đăng nhập với tài khoản thuy_user@gmail.com/123456 |  | 1. Login thành công 2. Thêm mới tài khoản user thành công 3. Ra màn hình login 4. Đăng nhập thành công, hiển thị chức năng ds sản phẩm và có thể thực hiện tìm kiếm sp ứng với role user. | Fail
Tinder-3
Tinder-4
Tinder-5
Tinder-6

## Add DM (hidden)
Module Code | AddDM | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 1 | 4 | 0 | 6 | [6 empty] | N/A
ID | Group Name | Sub Group Name | Test Case Description | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
AddDM-1 | <group of test case = big function> | <group of test case = medium function> | <group of test case = small function> |  | <Describe steps to perform this case> |  | <Describe results which meet customer's requirement> | Pass
AddDM-2 | Check display email | [6 empty] | Fail
AddDM-3
AddDM-4
AddDM-5
AddDM-6

## Login (hidden)
Module Code | Login | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 0 | 12 | 0 | 13 | [6 empty] | N/A
ID | Group Name | Sub Group Name | Test Case Description | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
Login-1 | Acess Right |  | Kiểm tra trường hợp copy link |  | 1. Paste link vào trình duyệt: https://test.warface.codegym.vn/admin/login 2. Nhấn Enter |  | 2. Hiển thị màn hình Login | Pass
Login-2 | UI |  | Kiểm tra số lượng Item | Đang ở màn hình login | Kiểm tra số lượng Item |  | Hiển thị chính xác các item: - Tên màn hình, tên trên tab html: Login - 2 textbox: Email và Password - 2 button: Login và Reset
Login-3 |  |  | Kiểm tra vị trí, font, size.... |  | Kiểm tra vị trí, font, size.... |  | Hiển thị chính xác như design
Login-4 |  |  | Kiểm tra trạng thái các item |  | Kiểm tra trạng thái các item |  | Các button đều ở trạng thái enable
Login-5 |  |  | Kiểm tra giá trị default |  | Kiểm tra giá trị default |  | Các mục textbox để trống
Login-6 | Business | Login | Login thành công | Đã tồn tại tài khoản admin@codegym.vn | 1. Input data - Email: admin@codegym.vn - Pass: 123123 2. Click button Login |  | 2. Login thành công và di chuyển vào trang Home page
Login-7 |  |  | Kiểm tra trường hợp Email không tồn tại | Trong hệ thống ko tồn tại email thuydl@gmail.com | 1. Input data - Email: thuydl@gmail.com - Pass: 123123 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Email không tồn tại trong hệ thốn"
Login-8 |  |  | Kiểm tra trường hợp Pass không đúng | Đã tồn tại tài khoản admin@codegym.vn/123123 | 1. Input data - Email: admin@codegym.vn - Pass: 123456 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Password không đúng"
Login-9 |  | Reset | Kiểm tra chức năng reset |  | 1. Nhập dữ liệu vào 2 mục Email/pass 2. Click button reset |  | 2. Clear hết dữ liệu đã nhập.
Login-10 | Validation | Email | Không nhập Email |  | 1. Input data - Email: Để trống - Pass: 123123 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Đây là trường bắt buộc nhập"
Login-11 |  |  | Nhập email thiếu @ |  | 1. Input data - Email: thuydlgmail.com - Pass: 123123 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Email bạn nhập không phải là email hợp lệ"
Login-12 |  |  | Nhập email không đúng định dạng xxx@xxx.xxx |  | 1. Input data - Email: admin@codegym - Pass: 123456 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Email bạn nhập không phải là email hợp lệ"
Login-13 |  | Password | Không nhập pass |  | 1. Input data - Email: admin@codegym.vn - Pass: Để trống 2. Click button Login |  | 2. Hệ thống hiển thị thông báo lỗi: "Đây là trường bắt buộc nhập"

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | Module1 | 1 | 1 | 6 |  | 6
| Sub total | 1 | 1 | 6 | 0 | 6
| Test coverage |  | 33.3333 | %
| Test successful coverage |  | 16.6667 | %

## Test report (hidden)
TEST REPORT
|  |  | Project Name |  | <Project Name> |  |  |  | Creator
|  |  | Project Code |  | <Project Code> |  |  |  | Reviewer/Approver
|  |  | Document Code |  | <Project Code>_Test Report_vx.x |  |  |  | Date
|  |  | Notes |  | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
I. Bug of Funtions
|  |  | No | Module code |  | Pass |  | Fail | Untesed |  | N/A | Number of test cases
|  |  | 1 | Login |  | 1 |  | 0 | 12 |  | 0 | 13
2
|  |  |  | Total |  | 1 |  | 0 | 12 |  | 0 | 13
|  |  |  | Test coverage |  |  | 7.692%
|  |  |  | Test successful coverage |  |  | 7.692%
II. Report by Defect
1. Classify Defect
|  | BugID | Bug/Nobug |  | Bug type | Cause of bug |  |  |  | Not-bug Classification |  |  |  | Action
|  | 1 | Bug |  | Functional | Coding mistake |  |  |  | As Specified
|  | 2 | No bug |  |  | Misunderstand Document |  |  |  | Duplicate
|  | 3 | Bug |  | UI | Error in Document |  |  |  | Insufficient execution environment
[6 empty] | Coding mistake |  |  |  | data error
[6 empty] | Misunderstand Document |  |  |  | Error in Testing procedure
[6 empty] | Unclear Document |  |  |  | Cannot Reproduce
[6 empty] | Error in Document |  |  |  | Connected system bad
[6 empty] | Coding mistake |  |  |  | Cause unknown
[6 empty] | Coding mistake |  |  |  | Cause unknown
[6 empty] | Misunderstand Document |  |  |  | requirement error
[6 empty] | Misunderstand Document |  |  |  | Other
Misunderstand Document
Coding mistake
Error in Document
Error in Document
Other
Other
2. Bug Analysis
Bug reason
| No |  |  | Reason |  |  |  |  | Number
| 1 |  |  | Coding mistake | [8 empty] | 5
| 2 |  |  | Misunderstand Document | [8 empty] | 5
| 3 |  |  | Unclear Document | [8 empty] | 1
| 4 |  |  | Error in Document | [8 empty] | 4
| 5 |  |  | Other | [8 empty] | 2
No bug
| No |  |  | Reason |  |  |  |  | Number
| 1 |  |  | As Specified | [8 empty] | 1
| 2 |  |  | Duplicate | [8 empty] | 1
| 3 |  |  | Insufficient execution environment | [8 empty] | 1
| 4 |  |  | data error | [8 empty] | 1
| 5 |  |  | Error in Testing procedure | [8 empty] | 1
| 6 |  |  | Cannot Reproduce | [8 empty] | 1
| 7 |  |  | Connected system bad | [8 empty] | 1
| 8 |  |  | Cause unknown | [8 empty] | 2
| 9 |  |  | requirement error | [8 empty] | 1
| 10 |  |  | Other | [8 empty] | 1