## Test Plan
Scope of testing
1. Functional requirements to perform test: -Login -Register -Forgot password -Newsfeed -My pages -Friend's pages -Other's pages -Edit profile -Search -Group -Common 2. Non-functional system testing: -Friendliness -Reliability 3. Eviroment to test: - Server test: https://social-network.warface.codegym.vn - Devices: Laptop,Mobile - Browsers: Chrome,Safari
Tool test
Test Plan : Google sheet Test Case: Google sheet Test database:My sql Tool to track bugs: Redmine Test report: Google sheet Test API:Postman Test performance:Jmeter Test sercurity: Burn Suite
Test approach
1. Method of building test case: - All functions and business of the system must write test cases 2. Test Browser and the devices are classified according to the following stages: - FUT: - Itegration test: - System test: 3. Method of using resources: - BA, review TC: All members - Test API, Test Functions, Test UI, Test Performance, Test Security: All members 4. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thuy |  | BA/Qc lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review test case - Responsible for the Business
2 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
3 | Others |  | Tester |  | - Write Test case - Write Test case for intergration test - Test API - Test UI - Test Function - Test Performance - Test Security
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan + Estimate | 3 | Tester | Test plan + Estimate | 25/10/2023
2 | Create requirement | 47 | Tester | Requirement | 28/10/2023
3 | Review requirement | 32.25 | Tester | Comment | 30/10/2023
4 | Create tescase | 63 | Tester | Test cases | 2023-01-11
5 | Review testcase | 40 | Tester | Comment | 2023-04-11
6 | Intergration testcase | 26.5 | Tester | Test cases | 2023-06-11
7 | Review intergration testcase | 26 | Tester | Comment | 2023-08-11
8 | Execution | 51.5 | Tester | Executed | 2023-11-11
9 | Log bug + Report | 67.8 | Tester | Bug + Report | 13/11/2023
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  | x | x | x
Functional Test |  |  | x | x | x
Performance Test
Usability test |  |  | x | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent |  |  | - End of Sprint - At the requests of Project Manager or superiors

## Estimate
No. | Pages | Sub-feature | Requirement |  |  | Test Case |  |  | Executed |  |  | Report | Total
|  |  | Create Req | Review Req | Update Req | Create TC | Review TC | Update TC | Test | Log bug | Phân tích bug | Report | (h) | (md)
1 | Login | Login | 1.5 | 1 | 1 | 1.5 | 1 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 9.5
2 | Register | Register | 3.5 | 3 | 2 | 6 | 4 | 2.5 | 4 | 2 | 1 | 0.5 | 28.5
3 | Forgot password | Forgot password | 2 | 1.5 | 0.5 | 2 | 2 | 0.5 | 1 | 1 | 0.5 | 0.5 | 11.5
4 | Search | - Search default - Search advance | 3 | 2.5 | 1.5 | 3.5 | 4 | 2 | 2 | 1.5 | 1 | 1 | 22
5 | Group | - Danh sách nhóm - Group timeline | 3 | 1.5 | 1.5 | 4 | 2 | 2 | 2.5 | 2 | 1 | 0.5 | 20
|  | - Group member - Group warning - Group participate | 4 | 3 | 2.5 | 5 | 3 | 2 | 3 | 2 | 2 | 2 | 28.5
6 | Newsfeed | Newsfeed | 2 | 1.5 | 0.5 | 3 | 2 | 1 | 3 | 0.5 | 1 | 0.5 | 15
7 | My page | My Pages | 4 | 2 | 1 | 4 | 3 | 2 | 3 | 1 | 1.5 | 1.5 | 23
8 | Other's pages | Other's pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 | 1 | 0.5 | 1.5 | 1.5 | 12
9 | Friend's pages | Friend's pages | 2 | 1.5 | 1 | 1.5 | 1 | 0.5 | 1 | 0.75 | 0.75 | 0.5 | 10.5
10 | Edit Profile | Edit profile | 2 | 1.5 | 1.5 | 2 | 1 | 1 | 2 | 1 | 0.5 | 0.8 | 13.3
|  | Change avatar | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 7.5
|  | Change password | 2 | 1 | 0.5 | 3 | 0.5 | 1 | 3 | 1 | 0.75 | 0.75 | 13.5
|  | Change status | 2 | 1 | 0.5 | 3 | 0.5 | 1 | 3 | 1 | 0.5 | 0.5 | 13
11 | Common | Header | 1 | 0.75 | 0.75 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 9
|  | Friend suggest | 2 | 1 | 1 | 1.5 | 1 | 0.5 | 1.5 | 1 | 1.5 | 1 | 12
|  | Advertisment | 1 | 0.5 | 0.25 | 1.5 | 1 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 7.75
|  | Chat | 2 | 1.5 | 1 | 2.5 | 2 | 1 | 2 | 1 | 1 | 1 | 15
|  | Create post | 2 | 1.5 | 1 | 1.5 | 1 | 1 | 3 | 1.5 | 1 | 1 | 14.5
|  | Post list | 2 | 1 | 1.5 | 2 | 1.5 | 1.5 | 3 | 1.5 | 1 | 1 | 16
|  | Comment+Reply+List | 3 | 2.5 | 2.75 | 4 | 3 | 2.75 | 2.5 | 1.5 | 1 | 1 | 24
12 | Intergration | Intergration |  |  |  | 8 | 4 | 2.5 | 6 | 2 | 2 | 2 | 26.5
Total |  |  | 47 | 32.25 | 23.75 | 63 | 40 | 27.25 | 51.5 | 25.75 | 22 | 20.05 | 352.55

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Sub total | #REF! | #REF! | #REF! | #REF! | #REF!
| Test coverage |  | #REF! | %
| Test successful coverage |  | #REF! | %