## Cover
Logo | TEST CASE
Project Name | Codegym_Tester_Shopping online |  |  | Creator
Project Code | CG_SO |  |  | Reviewer/Approver
Document Code | CG_SO_XXX_vx.x |  |  | Issue Date
|  |  |  | Version | 1.1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2021-11-07 | 1.0 |  | A | Tạo mới file | <List of documents which are referred in this version.>
30/7/2021 | 1.1 |  | M | Update ...

## Test Plan
Scope of testing
1. Functional requirements to perform test: - Login - Register - Forgot password - Search - Group - Add friends - New sfeed - My pages - Other's pages - Edit Profile 2. Non-functional system testing: - Performance, Usability 3. Eviroment to test: - Server test: https://social-network.warface.codegym.vn/login - Devices: Acef - Browsers: Chrome, Cốc cốc
Tools Test
Test Plan : Google sheet Test Case: Google sheet Tool to capture error images: Snapgit, Lightshot,.. Tool to track bugs: Redmine Test report: Google sheet Test performace: Jmeter Test API: Postman
Test approach
1. Method of building test case: - All functions and business of the system must write test cases 2. Test Browser and the devices are classified according to the following stages: - FUT: - Itegration test: - System test: 3. Method of using resources: - ThuyDL: BA, review TC - Hà, Uyên, Chi, Minh Anh, Phương, Vui, Yến, Thảo, Chinh, Huy: Test API, Test Functions, Test UI, Test Performance 4. Priority order to test: - Prioritize to test the screens which has had specification and has been coded - Prioritize to test the functions according to the milestones to be handed over to the customer:
Resources
No. | Name |  | Role |  | Task
1 | Thủy |  | BA/Qc lead |  | - Analyze requirements of project, synthesize related documents - Create test report - Create test plan - Review Test case - Responsible for the Business
2 | Minh Anh |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
3 | Uyên |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
4 | Chi |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
5 | Hà |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
6 | Huy |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
7 | Phương |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
8 | Vui |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
9 | Yến |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
10 | Thảo |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
11 | Chinh |  | Tester |  | Write spec, review spec - Write Test case, review test case, update test case - Test API - Test UI - Test Function - Test Performance
Deliverables and Milestons
No. | Milestone Task | Effort (Hour) | Assign to | Deliverables | Delivery date | Note
1 | Test plan | 6 | Test leader | Test plan | 2023-10-23
2 | Estimate | 2 | All Members | Estimate | 2023-10-24
3 | Spec | 50 | Tester | Spec | 2023-10-26
4 | Create TC | 55 | Tester | Create TC | 2023-10-29
5 | Execute TC | 50 | Tester | Execute TC | 2023-11-01
6 | Log bug | 30 | Tester | Log bug | 2023-11-07
Stage of Test
Test Types |  |  | Testing Levels
|  |  | Unit test | Integration | System | Acceptance
Interface Test |  |  |  | x | x | x
Functional Test |  |  |  | x | x | x
Performance Test |  |  |  |  | x | x
Usability test |  |  |  |  | x | x
Testing standard
Start condition test |  |  | - Code is reviewed and perform unit test
When stop test |  |  | - Complete test scope - All of identified bugs should be logged into an agreed solution. No more bugs with Nomal level and higher.
Standard success test |  |  | - Ensure that the functionality of the software is correctness - Ensure about non-function qualities: reliability, usablity, performance, sercurity. - Ensure that software appropriates to the requirements of users
When does test recurrent

## Test case List
TEST CASE LIST
Project Name |  | Codegym_Tester_Shopping online
Project Code |  | CG_SO
Test Environment Setup Description |  | <List enviroment requires in this system 1. Server 2. Database 3. Web Browser ... >
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Mail list | MailList
2 | Login | Sheet2
3 | Function C | Sheet3
4 | Function D | Sheet4
5 | Function E | Sheet5

## Template
Module Code | Module1 | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 1 | 4 | 0 | 6 | [6 empty] | N/A
ID | Group Name | Sub Group Name | Test Case Description | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
Module1 -1 | <group of test case = big function> | <group of test case = medium function> | <group of test case = small function> |  | <Describe steps to perform this case> |  | <Describe results which meet customer's requirement> | Pass
Module1 -2 | Check display email | [6 empty] | Fail
Module1 -3
Module1 -4
Module1 -5
Module1 -6

## Add DM
Module Code | AddDM | [9 empty] | Pass
Test requirement | <Brief description about requirements which are tested in this sheet> | [9 empty] | Fail
Tester
Pass | Fail | Untested | N/A | Number of Test cases | [6 empty] | Untesed
1 | 1 | 4 | 0 | 6 | [6 empty] | N/A
ID | Group Name | Sub Group Name | Test Case Description | Precondition | Test Case Procedure | Test data | Expected Output | Result | Test date | Note
AddDM-1 | <group of test case = big function> | <group of test case = medium function> | <group of test case = small function> |  | <Describe steps to perform this case> |  | <Describe results which meet customer's requirement> | Pass
AddDM-2 | Check display email | [6 empty] | Fail
AddDM-3
AddDM-4
AddDM-5
AddDM-6

## Test Report 1 (hidden)
TEST REPORT
Project Name | <Project Name> |  | Creator
Project Code | <Project Code> |  | Reviewer/Approver
Document Code | <Project Code>_Test Report_vx.x |  | Issue Date |  |  | <Date when this test report is created>
Notes | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | Module1 | 1 | 1 | 6 |  | 6
| Sub total | 1 | 1 | 6 | 0 | 6
| Test coverage |  | 33.3333 | %
| Test successful coverage |  | 16.6667 | %

## Test report
TEST REPORT
|  |  | Project Name |  | <Project Name> |  |  |  | Creator
|  |  | Project Code |  | <Project Code> |  |  |  | Reviewer/Approver
|  |  | Document Code |  | <Project Code>_Test Report_vx.x |  |  |  | Date
|  |  | Notes |  | <List modules included in this release> ex: Release 1 includes 2 modules: Module1 and Module2
I. Bug of Funtions
|  |  | No | Module code |  | Pass |  | Fail | Untesed |  | N/A | Number of test cases
|  |  | 1 | #REF! |  | #REF! |  | #REF! | #REF! |  | #REF! | #REF!
2
|  |  |  | Total |  | #REF! |  | #REF! | #REF! |  | #REF! | #REF!
|  |  |  | Test coverage |  |  | #REF!
|  |  |  | Test successful coverage |  |  | #REF!
II. Report by Defect
1. Classify Defect
|  | BugID | Bug/Nobug |  | Bug type | Cause of bug |  |  |  | Not-bug Classification |  |  |  | Action
|  | 1 | Bug |  | Functional | Coding mistake |  |  |  | As Specified
|  | 2 | No bug |  |  | Misunderstand Document |  |  |  | Duplicate
|  | 3 | Bug |  | UI | Error in Document |  |  |  | Insufficient execution environment
[6 empty] | Coding mistake |  |  |  | data error
[6 empty] | Misunderstand Document |  |  |  | Error in Testing procedure
[6 empty] | Unclear Document |  |  |  | Cannot Reproduce
[6 empty] | Error in Document |  |  |  | Connected system bad
[6 empty] | Coding mistake |  |  |  | Cause unknown
[6 empty] | Coding mistake |  |  |  | Cause unknown
[6 empty] | Misunderstand Document |  |  |  | requirement error
[6 empty] | Misunderstand Document |  |  |  | Other
Misunderstand Document
Coding mistake
Error in Document
Error in Document
Other
Other
2. Bug Analysis
Bug reason
| No |  |  | Reason |  |  |  |  | Number
| 1 |  |  | Coding mistake | [8 empty] | 5
| 2 |  |  | Misunderstand Document | [8 empty] | 5
| 3 |  |  | Unclear Document | [8 empty] | 1
| 4 |  |  | Error in Document | [8 empty] | 4
| 5 |  |  | Other | [8 empty] | 2
No bug
| No |  |  | Reason |  |  |  |  | Number
| 1 |  |  | As Specified | [8 empty] | 1
| 2 |  |  | Duplicate | [8 empty] | 1
| 3 |  |  | Insufficient execution environment | [8 empty] | 1
| 4 |  |  | data error | [8 empty] | 1
| 5 |  |  | Error in Testing procedure | [8 empty] | 1
| 6 |  |  | Cannot Reproduce | [8 empty] | 1
| 7 |  |  | Connected system bad | [8 empty] | 1
| 8 |  |  | Cause unknown | [8 empty] | 2
| 9 |  |  | requirement error | [8 empty] | 1
| 10 |  |  | Other | [8 empty] | 1